## Product Backlog
Project Name | OrangeHRM
Client
Created By | Kanchan ghute
Creation Date | 2025-05-30
Approval Date
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
Epic-1 | US_01 | Verify the login functionality when a user enter a Lowercase characters of login ID and correct Password | A popup box of an error message(CSRF token validation failed ) | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_02 | Verify the login functionality with Only all uppercase characters of id and correct password. | A popup box of an error message | Fail(Done) | 1.Enter valid user name & Invalid Password 2.Click on login button 3.A popup box of an error message
| US_03 | Verify the login functionality When Numarics of userid and correct password. | A popup box of an error message.(CSRF token validation failed ) | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_04 | Verify the login functionality of special characters of userID and password | A popup box of an error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_05 | Verify the login functionality of valid userID and valid password | Land on Home page | Done | 1.Enter valid username & Password 2.Click on login button 3. Navigate to the home page
| US_06 | Verify the login functionality of valid userID and upper case characters of password | A popup box of an error message(Invalid credentials ) | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_07 | Verify the login functionality of valid userID and lower case characters of password | Land on Home page and to see the HOME PAGE | Done | 1.Enter invalid username &valid password 2.Click on login button 3.Navigate to the home page
| US_08 | Verify the login functionality valid Userid and numarics of password | A popup box of an error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_09 | Verify the login functionality valid Userid and two times ofpassword | A popup box of an error message(Invalid credentials) | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_10 | Verify the behavior of the login functionality when a user enter a invalid ID | A popup box of an error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_11 | Enter the user id with all lower case letter | succesfully login to homepage | Done | 1.Enter valid username with all lower case letters &valid password 2.Click on login button 3.Successfully login on home page by showing all products
| US_12 | Enter the user id with all upper case letter | A popup box of an error message | Done | 1.Enter valid username with all upper case letters &valid password 2.Click on login button 3.A pop up box of an error message
| US_13 | Verify the behavior of the login functionality when a user enter a valid password for their login | succesfully login to homepage | Done | 1.Enter valid username &valid password 2.Click on login button 3.Successfully login on home page by showing all products
| US_14 | User able to find filter option and able to click on filter option | Search for filter option, wheather it is displaying or not , and click on it | Done | 1.Check for filter, wheather it is displaying or not. 2.Click on filter button wheather it is working or not properly and displaying filter options properly or not
| US_15 | User able to click on filter option and able to click on alphabet option | Search for filter option and click on it,select the option according to Alphabets,click on it. | Done | 1.Click on filter option. 2.Click on Name(A to Z) option. 3.Click on Name(A to Z).
| US_16 | Size option | user unable to find the size option in filters | Done | 1.Click on filter option. 2.Click on size option.
| US_17 | Side menu bar | User able open the "side menu bar" | Done | 1.Click on side menu bar, opens side menu bar.
| US_18 | My account | User able to find an option called my info in side menu bar | Done | 1.Click on side menu bar, opens side menu bar.
| US_19 | performance | User able to find an option called performance in side menu bar | Done | 1.Click on side menu bar, opens side menu bar.
| US_20 | side arow mark in side menu bar | User able close the "side menu bar" | Done | 1.Click on side arow mark in side menu bar, closes side menu bar.
| US_21 | User is able to click on PIM | validate the"PIM" | Done | 1.User should click on PIM/title 2.Clickling on should navigate to the employee details
| US_22 | User is able click on add employee | add employee management | Done | 1.User should click on PIM/title 2.Clicking on them it added to the add employee
| US_23 | User is able to see add employee by click on employee list | new employee add in employee list | Done | 1.User should click on PIM/title 2.Clickling on employee list
| US_24 | User is able to see employee details | see the employee details | Done | 1.User should click on PIM/title 2.Clickling on should employee list 3.click on action menu
| US_31 | User is able to click on product image | Checking the image is visible larger or not | Done | 1.Product image are clickable. 2 Clickling on an image displays a larger image. 3.Enlarger image results detailed view of product
| US_32 | User is able to click on product image | Clicking on product navigate to corresponding page | Done | 1.Product image are clickable 2. Navigate to corresponding page
| US_33 | User able to remove single item from the cart | Removing single item from the cart | Done | Item to be added to the cart for testing the removal functionality
| US_34 | User able to select multiple items to remove the cart | Checking Multiple items at a time can be removed from the cart | Done | Item to be added to the cart for testing the removal functionality
| US_35 | User able to view product details completely by click on product name in the cart | Viewing the product details | Done | Item to be added to the cart for testing the removal functionality
| US_36 | User is able to click on Add to Cart Functionality | As a user, I want to be able to add items to the cart | Done | 1. Clicking "Add to Cart" adds the item to the cart 2. After adding the item, the option changes to "Remove from Cart"
| US_37 | User is able to click on Cart Image Functionality | User want to be able to open the cart from the cart icon | Done | 1. Clicking "Cart icon" moves the page to cart
| US_38 | User is able to Click on Cart to check correct no of items are added or not | User is able to click on a product to add to cart | Done | 1.Clicking on the product which the user want to add to cart
| US_39 | User is able to Click on Cart to see correct item is added or not | User is able to click on cart and able to check the product | Done | 1.User should click on the cart 2.click the product is added or not
| US_40 | User is able to check product image is visible or not | User is able to click cart image | Done | 1.Clicking on the product Image
Epic-1 | US_41 | User is able to check cart consists of items or empty | User is able to click cart image | Done | 1.Clicking on Cart Image
| US_42 | User is able to increase the quantity of the product | User is able to increase the quantity of the product | Done | 1.Clicking on Cart Image 2.Click on try to increase the quantity of product
| US_43 | User is able to check Quantity of product | User is able to see the quantity of the product | Done | 1.Clicking on Cart Image 2.Click on product and check the quantity of the product which the buyer want to order
| US_44 | User is able to access previous page from the cart page | User is able to access the previous page from the cart page | Done | 1.Clicking on cart page 2.Click on cart image 3.Click on continue shopping for Previous page
| US_45 | User is able to click Cart Icon | User want to be able to open the cart from the cart icon | Done | 1.Clicking on cart page 2.Click on cart image

## Sprint Planning
Project Name | OrangeHRM
Client | Excel R
Created By | kanchan ghute
Attendees | kanchan ghute
Creation Date | 2025-05-30
Epic | User Story ID | Feature/Title | User Story | Sprint | Status | Acceptance Creteria
Epic_01
| US_ID01 | Verify the login functionality when a user enter a Lowercase characters of login ID and correct Password | A popup box of an error message(CSRF token validation failed) | SP_01 | DONE | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_ID02 | Verify the login functionality with Only all uppercase characters of id and correct password. | A popup box of an error message | SP_01 | DONE | 1.Enter valid user name & Invalid Password 2.Click on login button 3.A popup box of an error message
| US_ID03 | Verify the login functionality When Numarics of userid and correct password. | A popup box of an error message.(CSRF token validation failed) | SP_01 | DONE | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_ID04 | Verify the login functionality of special characters of userID and password | A popup box of an error message | SP_01 | DONE | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_ID05 | Verify the login functionality of valid userID and valid password | Land on Home page and to see the products | SP_01 | DONE | 1.Enter valid username & Password 2.Click on login button 3. Navigate to the home page
| US_ID06 | Verify the login functionality of valid userID and upper case characters of password | A popup box of an error message(Invalid credentials) | SP_01 | DONE | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_ID07 | Verify the login functionality of valid userID and lower case characters of password | Land on Home page and to see the HOME PAGE | SP_01 | DONE | 1.Enter invalid username &valid password 2.Click on login button 3.Navigate to the home page
| US_ID08 | Verify the login functionality valid Userid and numarics of password | A popup box of an error message | SP_01 | DONE | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_ID09 | Verify the login functionality valid Userid and two times ofpassword | A popup box of an error message(Invalid credentials) | SP_02 | DONE | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_ID010 | Verify the behavior of the login functionality when a user enter a invalid ID | A popup box of an error message | SP_02 | DONE | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| US_ID011 | Enter the user id with all lower case letter | succesfully login to homepage | SP_02 | DONE | 1.Enter valid username with all lower case letters &valid password 2.Click on login button 3.Successfully login on home page by showing all products
| US_ID012 | Enter the user id with all upper case letter | A popup box of an error message | SP_02 | DONE | 1.Enter valid username with all upper case letters &valid password 2.Click on login button 3.A pop up box of an error message
| US_ID013 | Verify the behavior of the login functionality when a user enter a valid password for their login | succesfully login to homepage | SP_02 | DONE | 1.Enter valid username &valid password 2.Click on login button 3.Successfully login on home page by showing all products
| US_ID014 | User able to find filter option and able to click on filter option | Search for filter option, wheather it is displaying or not , and click on it | SP_02 | DONE | 1.Check for filter, wheather it is displaying or not. 2.Click on filter button wheather it is working or not properly and displaying filter options properly or not
| US_ID015 | User able to click on filter option and able to click on alphabet option | Search for filter option and click on it,select the option according to Alphabets,click on it. | SP_02 | DONE | 1.Click on filter option. 2.Click on Name(A to Z) option. 3.Click on Name(A to Z).
| US_ID016 | Size option | user unable to find the size option in filters | SP_02 | DONE | 1.Click on filter option. 2.Click on size option.
| US_IDO17 | Side menu bar | User able open the "side menu bar" |  | DONE | 1.Click on side menu bar, opens side menu bar.
| US_IDO18 | My account | User able to find an option called my info in side menu bar |  | DONE | 1.Click on side menu bar, opens side menu bar.
| US_IDO19 | performance | User able to find an option called performance in side menu bar |  | DONE | 1.Click on side menu bar, opens side menu bar.
| US_IDO20 | side arow mark in side menu bar | User able close the "side menu bar" |  | DONE | 1.Click on side arow mark in side menu bar, closes side menu bar.
| US_IDO21 | User is able to click on PIM | validate the"PIM" |  | DONE | 1.User should click on PIM/title 2.Clickling on should navigate to the employee details
| US_IDO22 | User is able click on add employee | add employee management |  | DONE | 1.User should click on PIM/title 2.Clicking on them it added to the add employee
| US_IDO23 | User is able to see add employee by click on employee list | new employee add in employee list |  | DONE | 1.User should click on PIM/title 2.Clickling on employee list
| US_IDO24 | User is able to see employee details | see the employee details |  | DONE | 1.User should click on PIM/title 2.Clickling on should employee list 3.click on action menu

## Test scenarios
,
Project Name | OrengeHRM
Module Name | OrangeHRM_Test_cases
Requirement Number | REQ001
Test case Type | Functionality , Usability , Performance Testings
Reference Doccument | NA
Pre-condition | OrangeHRM URL should be accessible
Test Data | https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
Test Senario number | Description | Test Scenario Type | TE Name
User Story 1- KANCHAN
TSH_01 | Verify the login functionality when a user enter a Lowercase characters of login ID and correct Password | Functional Testing | KANCHAN
TSH_02 | Verify the login functionality with Only all uppercase characters of id and correct password. | Functional Testing | KANCHAN
TSH_03 | Verify the login functionality When Numarics of userid and correct password. | Functional Testing | KANCHAN
TSH_04 | Verify the login functionality of special characters of userID and password | Functional Testing | KANCHAN
TSH_05 | Verify the login functionality of valid userID and valid password | Functional Testing | KANCHAN
TSH_06 | Verify the login functionality of valid userID and upper case characters of password | Functional Testing | KANCHAN
TSH_07 | Verify the login functionality of valid userID and lower case characters of password | Functional Testing | KANCHAN
TSH_08 | Verify the login functionality valid Userid and numarics of password | Functional Testing | KANCHAN
User Story 2- KANCHAN
TSH_09 | Verify the login functionality valid Userid and two times of password | Functional Testing | KANCHAN
TSH_10 | Verify the behavior of the login functionality when a user enter a invalid ID | Functional Testing | KANCHAN
TSH_11 | Enter the user id with all lower case letter | Functional Testing | KANCHAN
TSH_12 | Enter the user id with all upper case letter | Functional Testing | KANCHAN
TSH_13 | Verify the behavior of the login functionality when a user enter a valid password for their login | Functional Testing | KANCHAN
TSH_14 | User able to find filter option and able to click on filter option | Usability Testing | KANCHAN
TSH_15 | User able to click on filter option and able to click on alphabet option | Usability Testing | KANCHAN
TSH_16 | Size option | Usability Testing | KANCHAN
User Story 3-KANCHAN
TSH_17 | Side menu bar | Usability Testing | KANCHAN
TSH_18 | My account | Usability Testing | KANCHAN
TSH_19 | performance | Performance Testings | KANCHAN
TSH_20 | side arow mark in side menu bar | Performance Testings | KANCHAN
TSH_21 | User is able to click on PIM | Performance Testings | KANCHAN
TSH_22 | User is able click on add employee | Performance Testings | KANCHAN
TSH_23 | User is able to see add employee by click on employee list | Performance Testings | KANCHAN
TSH_24 | User is able to see employee details | Performance Testings | KANCHAN
User Story 5-Gayathri Priya

## Test cases
TE Name | Test case number | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date | DEFECT NO
KANCHAN | TC_01 | Verify the login functionality of OrangeHRM when a user enter a Lowercase characters of login ID and correct Password | Verify the behavior of the login functionality when a user enter only lowercase characters of login ID and validPassword then click on login button. | 1.Open the OrangeHRM application 2. Enter all lowercase charactersof user ID. 3.Enter valid password. 4.Click on login button. | UserID : admin Password:admin123 | Error message | A pop up box of an error message | Medium | High | kanchan | pass | 2025-05-30 | 2025-05-30
KANCHAN | TC_02 | Verify the login functionality of OrangeHRM when a user enter with Only all uppercase characters of id and correct password. | Verify the behavior of the login functionality when a user enter only all uppercase characters of loginID and valid password then click on login button. | 1.open the OrangeHRM application 2. Enter all uppercase characters of userID. 3.Enter valid password. 4.Click on login button. | UserID:ADMIN Password:admin123 | A pop up box of an error message | Should land on Home page | High | Medium | kanchan | Fail | 2025-05-30 | 2025-05-30 | TC_02_DT_001
KANCHAN | TC_03 | Verify the login functionality of OrangeHRM when a Numarics of userid and correct password. | Verify the behavior of the login functionality when a user enter Numarics of loginID and valid password then click on login button. | 1.open the OrangeHRM application 2.Enter invalid username &valid password 3.Click on login button 4.A pop up box of an error message | UserID:12345 Password:admin123 | A pop up box of an error message | A popup box of an error message.(CSRF token validation failed ) | Medium | High | kanchan | pass | 2025-05-30 | 2025-05-30
KANCHAN | TC_04 | Verify the login functionality of OrangeHRM when a special characters of userID and password | Verify the behavior of the login functionality when a user enter special characters of userID and password | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message | UserID:Admin@123 Password:admin123 | A pop up box of an error message | A popup box of an error message.(CSRF token validation failed ) | Medium | High | kanchan | pass | 2025-05-30 | 2025-05-30
KANCHAN | TC_05 | Verify the login functionality of OrangeHRM when a valid userID and valid password | Verify the behavior of the login functionality when a valid userID and valid password | 1.Enter valid username & Password 2.Click on login button 3. Navigate to the home page | UserID:Admin Password:admin123 | Land on Home page and to see the products | Land on Home page and to see the products | High | High | kanchan | pass | 2025-05-30 | 2025-05-30
KANCHAN | TC_06 | Verify the login functionality of OrangeHRM when a valid userID and upper case characters of password | Verify the behavior of the login functionality when a valid userID and upper case characters of password | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message | UserID:Admin Password:ADMIN123 | A pop up box of an error message | A pop up box of an error message | Medium | High | kanchan | pass | 2025-05-30 | 2025-05-30
KANCHAN | TC_07 | Verify the login functionality of OrangeHRM when a valid userID and lower case characters of password | Verify the behavior of the login functionality when a valid userID and lower case characters of password | 1.Enter invalid username &valid password 2.Click on login button 3.Navigate to the home page | UserID:Admin Password:admin123 | Land on Home page and to see the HOME PAGE | Land on Home page and to see the HOME PAGE | High | High | kanchan | pass | 2025-05-30 | 2025-05-30
KANCHAN | TC_08 | Verify the login functionality of OrangeHRM when a valid Userid and numarics of password | Verify the behavior of the login functionality when a valid Userid and numarics of password | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message | UserID:Admin Password:123 | A popup box of an error message(Invalid credentials) | A popup box of an error message(Invalid credentials) | High | High | kanchan | pass | 2025-05-30 | 2025-05-30

## Defects
TE Name | Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to | Screen Shots
Kanchan | DEF001 | OrengeHRM | Click on login button | REQ001 | TC_002 | Click on login button | 1.open the OrangeHRM application 2. Enter all uppercase characters of userID. 3.Enter valid password. 4.Click on login button. | when entering all uppercase character of user id and valid password it requried to show an error message and don't opening to the homepage | High | Medium

## Defect_Snapshots
Defect ID | Test Case ID | Failed Screenshots
DEF001 | TC_002

## Test excution details
Test Case ID | Test Case Name | Screenshots | TestCase Execution Date | TestCase Execution Start Time | TestCase Execution END Time
TC_01 | Verify the login functionality of OrangeHRM when a user enter a uupercase characters of login ID and correct Password |  | 2025-05-30 | 13:40 | 17:55
TC_62

## Story_Point_Effort_and_Reason
User Story1-KANCHAN
Project Name :- | OrangeHRM
Story Point :- | 8
Reason for story point :- | User is able to click on login button and to see home page
Efforts(in hours) :- | 3
Reason for Efforts :- | Test cases Preparation:24 Test case excecution:8 Raising Bugs:1
Project Name :-
Story Point :-
Reason for story point :-
Efforts(in hours) :-
Reason for Efforts :-
Project Name :-
Story Point :-
Reason for story point :-
Efforts(in hours) :-
Reason for Efforts :-
Project Name :-
Story Point :-
Reason for story point :-
Efforts(in hours) :-
Reason for Efforts :-
Project Name :-
Story Point :-
Reason for story point :-
Efforts(in hours) :-
Reason for Efforts :-

## Test report
SNO | TE NAME | TOTAL TEST CASE | PASS | FAIL | BLOCKERS | NOT EXECUTED | PASS RATIO (%) formula use : D2/C2*100 | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
1 | KANCHAN | 8 | 7 | 1 | 0 | 0 | 87.5 | 0 | 0 | 10 | 1
TOTAL |  | 8 | 9 | 1 | 0 | 0 | 87.5 | 0 | 0 | 10 | 1